## Sheet1
Blanket Closure Order South Area
From 7th February 2022 to 31st March 2022 the following roads will be subject to temporary traffic orders as per the details listed below. Advanced Warning of dates to be displayed by signs on site.
Scheme Number | Road Name | Closure Extent (From) | Closure Extent (To) | Parish | Closure Length (m) | Treatment | Type of Closure | Type of Restriction | Cost Code
42379384 | 3/358 Station Road, Berkeley | B4066 | Halmore Lane | Berkeley | 1600 | Patching | Closure & No Parking/Waiting during All/Part of the Works | UNRESTRICTED DAYS | Y-1000-44492R
43074876 | B4066 Berkeley Bypass | CANONBURY STREET | STATION ROAD | BERKELEY | 800 | Patching | Closure & No Parking/Waiting during All/Part of the Works | UNRESTRICTED DAYS | Y-1000-44492R
43076421 | 3/268 and 3/267 Bear Hill to The Butts | BEAR HILL | PRIVATE ROAD | RODBOROUGH | 500 | Patching | Closure & No Parking/Waiting during All/Part of the Works | UNRESTRICTED DAYS | Y-1000-44492R
42379348 | 47579 Lower Spillmans | BATH ROAD | RODBOROUGH HILL | RODBOROUGH | 500 | Patching | Closure & No Parking/Waiting during All/Part of the Works | UNRESTRICTED DAYS | Y-1000-44492R
43076048 | 3/268 Cirencester Road, Minchinhampton | THE KNAPP | HAMPTON ROAD | MINCHINHAMPTON | 1400 | Patching | Closure & No Parking/Waiting during All/Part of the Works | UNRESTRICTED DAYS | Y-1000-44492R
43076058 | 41287 Coppice Hill | RANDALLS GREEN | DR MIDDLETONS ROAD | CHALFORD | 1000 | Patching | Closure & No Parking/Waiting during All/Part of the Works | UNRESTRICTED DAYS | Y-1000-44492R
43076051 | 41324 Middle Hill, Chalford | BURCOMBE ROAD | MIDDLE HILL CRESENT | CHALFORD | 500 | Patching | Closure & No Parking/Waiting during All/Part of the Works | UNRESTRICTED DAYS | Y-1000-44492R
42402066 | 41424 ST MARYS HILL, Woodchester | A46 BATH ROAD | PARK LANE | WOODCHESTER | 400 | Patching | Closure & No Parking/Waiting during All/Part of the Works | UNRESTRICTED DAYS | Y-1000-44492R
42402258 | 41590 Southbank Woodchester | SOUTHFIELD ROAD | CHURCH ROAD | WOODCHESTER | 200 | Patching | Closure & No Parking/Waiting during All/Part of the Works | UNRESTRICTED DAYS | Y-1000-44492R
43076248 | 51401 Downton Farm Lane, Frocester | PETERS STREET | DEAD END | FROCESTER | 600 | Patching | Closure & No Parking/Waiting during All/Part of the Works | UNRESTRICTED DAYS | Y-1000-44492R
42401789 | 47682 MELBOURNE CLOSE, Stonehouse | MELBOURNE DRIVE | DEAD END | STONEHOUSE | 200 | Patching | Closure & No Parking/Waiting during All/Part of the Works | UNRESTRICTED DAYS | Y-1000-44492R
42398853 | 41115 STICKY LANE, Hardwicke | GREEN LANE | DEAD END | HARDWICKE | 500 | Patching | Closure & No Parking/Waiting during All/Part of the Works | UNRESTRICTED DAYS | Y-1000-44492R
42398925 | 47504 BISLEY ROAD | HOLLOWAY LANE | BISLEY OLD ROAD | STROUD | 1600 | Patching | Closure & No Parking/Waiting during All/Part of the Works | UNRESTRICTED DAYS | Y-1000-44492R
42398870 | 47603 ROWCROFT RETREAT | A46 MERRYWALKS | KING STREET | STROUD | 600 | Patching | Closure & No Parking/Waiting during All/Part of the Works | UNRESTRICTED DAYS | Y-1000-44492R
| 41620 Standle Lane | ECHO LANE | DEAD END | STINCHCOMBE | 1000 | Patching | Closure & No Parking/Waiting during All/Part of the Works | UNRESTRICTED DAYS | Y-1000-44492R
| 41480 Coombe Lane | Holywell Road | Coombe Village Road | WOTTON UNDER EDGE | 500 | Patching | Closure & No Parking/Waiting during All/Part of the Works | UNRESTRICTED DAYS | Y-1000-44492R
| B4071 Bridge Road | LAKE LANE | CANAL BRIDGE | FRAMPTON | 250 | Patching | Closure & No Parking/Waiting during All/Part of the Works | UNRESTRICTED DAYS | Y-1000-44492R
42401798 | 41279 Moons Lane (ROAD FROM HYDES BOTTOM TO SOLOMONS COURT), Oakridge/Bisley | HYDES BOTTOM | SOLOMANS COURT | BISLEY | 800 | Patching | Closure & No Parking/Waiting during All/Part of the Works | UNRESTRICTED DAYS | Y-1000-44492R